**Statement of work**

By **Expert Software Solution**

For **Hello Developers LTD**

**Date:** 24-01-2025

**SOW:** 01

## ****Introduction****

Expert Software Solution will deliver a **Dynamic Web Application** for Hello Developers LTD.

**Purpose and Objectives**

The purpose of this project is to design and develop a user-friendly, scalable, and dynamic web application.  
**Objectives:**

1. Build an interactive front-end for seamless user experiences.
2. Develop a robust back-end for managing dynamic content and data processing.
3. Ensure security, performance optimization, and scalability.

**Tasks**

Expert Software Solution will complete the following tasks:

1. **Project Planning**: Outline goals, timelines, and resource allocation.
2. **Requirement Gathering**: Collaborate with stakeholders to finalize the scope.
3. **UI/UX Design**: Design a visually appealing and intuitive interface.
4. **Development**:
   * Back-end: Develop APIs and database systems.
   * Front-end: Integrate designs and functionalities.
5. **Testing**: Conduct unit, integration, and user acceptance testing.
6. **Deployment**: Deploy the application to the designated server.

**Out-of-Scope Tasks**

The following tasks are not included in this project:

* Data migration for pre-existing systems.
* Post-deployment maintenance and support.

**Deliverables**

Expert Software Solution will provide the following deliverables:

1. Complete UI/UX designs.
2. Fully functional and tested dynamic web application.
3. Deployment files, along with technical documentation.

**Schedule**

This project will follow the estimated timeline below:

|  |  |  |  |
| --- | --- | --- | --- |
| Task/Project Phase | Estimated Start Date | Estimated End Date | Estimated Hours |
| Project Planning | 01-02-2025 | 07-02-2025 | 20 hours |
| Requirement Gathering | 08-02-2025 | 15-02-2025 | 40 hours |
| UI/UX Design | 16-02-2025 | 29-02-2025 | 60 hours |
| Development | 01-03-2025 | 30-04-2025 | 200 hours |
| Testing | 01-05-2025 | 15-05-2025 | 40 hours |
| Deployment | 16-05-2025 | 20-05-2025 | 10 hours |

**Location**

All work related to this project will occur at office. Expert Software Solution will not perform work at remote or home.

**Budget, Pricing, and Payment Schedule**

Hello Developers LTD has a total budget of **$25,000** for this project, not to be exceeded.

Expert Software Solution will charge the following rates per deliverable:

|  |  |
| --- | --- |
| Deliverable | Price |
| UI/UX Design | $ $7,500 |
| Web Application Development | $10,000 |
| Final Application Delivery | $ $7,500 |

**Payment Terms:**

1. 30% upfront payment before project commencement.
2. 40% upon delivery of the developed application.
3. 30% upon successful deployment.

**Resources**

Hello Developers LTD will provide:

1. Access to hosting or cloud servers.
2. Domain credentials.
3. Required APIs for integration.

**Special Terms and Conditions**

1. Deliverables will be reviewed and signed off within 7 business days of submission.
2. Any additional work outside the agreed scope requires a formal change request and may incur extra charges.
3. Intellectual property rights for the delivered software will belong to Hello Developers LTD.

**Signatures**

Signed and agreed to by:

Expert Software Solution

Md Sajedur Rahman

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: 24-01-2025

Hello Developers Limited

Md Mahamud Hasan

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: 24-01-2025